## Sprint Backlog
ID | Screen / Epic | Priority | As a... | I want to... | So that... | Acceptance Criteria | Development Tasks | Story Points | Sprint | Status | Estimated Time (hrs) | Source
FND-1 | Foundation | 1 | Developer | a JavaFX project with a scene manager that switches between the three screens | every screen shares one navigation path and one window | App launches on Login; scene manager can load Login, Device Selection and Admin Dashboard FXML views; session holds the signed-in user. | Create Maven/Gradle JavaFX project; build SceneManager; build Session class; stub 3 FXML views. | 3 | Sprint 1 | Not Started | 0.5 | New
FND-2 | Foundation | 1 | Developer | domain classes for User, Device, Department, Building, Role and DeviceStatus | all screens use the same data model | Device holds asset ID, serial number, type, manufacturer, model, department, building, room, status, assigned user, checkout date, due date and allowed roles. Status limited to Active/Repairable/Broken. | Write model classes and enums; add validation in constructors/setters; add equals/hashCode on asset ID. | 3 | Sprint 1 | Not Started | 0.5 | Refined (README: Device records)
FND-3 | Foundation | 1 | Developer | a repository layer for users and devices | screens can create, read, update and delete records without knowing the storage details | DeviceRepository and UserRepository support CRUD; swappable between in-memory and file/DB storage; duplicate asset ID or serial number rejected. | Define repository interfaces; implement in-memory version; add duplicate checks. | 3 | Sprint 1 | Not Started | 0.5 | New
FND-4 | Foundation | 1 | Developer | seed sample users and devices on startup | the screens can be demonstrated and tested right away | At least 2 students, 2 staff, 2 professors, 1 admin; 15+ devices across all departments and several buildings; at least one overdue assignment. | Create SeedData class with sample users (valid westga.edu emails) and devices. | 2 | Sprint 1 | Not Started | 0.5 | New
FND-5 | Foundation | 1 | Developer | unit tests for the core business rules | email, overdue and role-eligibility rules are verified before the GUI uses them | Tests pass for: westga.edu validation, overdue check, role-eligibility check, status validation, available-device check. | Write JUnit tests; create ValidationService, EligibilityService. | 3 | Sprint 1 | Not Started | 0.5 | Refined (README: Core Rules)
LOG-1 | Login | 1 | University User (Student/Staff/Professor) | sign in with my university email and password | I can securely access the inventory system | Login screen has email, password (masked), department selector and Sign In button. Valid credentials open the correct next screen; invalid credentials show a message and stay on Login. | Build login.fxml; build LoginController; add AuthService to check credentials against UserRepository. | 3 | Sprint 1 | Not Started | 0.5 | README P1: sign in
LOG-2 | Login | 1 | University User (Student/Staff/Professor) | have the system validate that my email ends in westga.edu | only users with valid university credentials can use protected features | Email is trimmed and checked case-insensitively; anything not ending in westga.edu is rejected with "Please use your westga.edu email address" before any credential check. | Implement isValidUniversityEmail(); wire to Sign In and to field-level validation. | 2 | Sprint 1 | Not Started | 0.5 | README P1: validate email
LOG-3 | Login | 1 | University User (Student/Staff/Professor) | choose my department from a fixed list when signing in | my device assignments are tied to the correct department | Dropdown shows the set list of departments (see Reference Data); required for students, staff and professors; selected department is stored in the session. | Add ComboBox populated from Department enum; require selection; save to Session. | 2 | Sprint 1 | Not Started | 0.5 | README P1: department at sign-in
LOG-4 | Login | 1 | University User (Student/Staff/Professor) | send administrators to the admin dashboard and everyone else to device selection | I only see the screen meant for my role | Admin role opens Admin Dashboard; Student, Staff and Professor open Device Selection; admins are not forced to choose a department. | Add role-based routing in LoginController using SceneManager. | 3 | Sprint 1 | Not Started | 0.5 | Refined (README P3: roles)
LOG-5 | Login | 4 | University User (Student/Staff/Professor) | see validation messages for blank or invalid fields | I can correct my information before submitting | Blank email, blank password or missing department each show an inline message; Sign In stays disabled or blocked until fixed; password is never shown in messages. | Add inline error labels; add field-level checks in controller. | 2 | Sprint 2 | Not Started | 0.5 | README P4: validation messages
LOG-6 | Login | 3 | University User (Student/Staff/Professor) | sign out from any screen | the next person using the computer cannot access my account | Sign Out button on Device Selection and Admin Dashboard clears the session and returns to Login. | Add Sign Out button; add Session.clear(); navigate to Login. | 1 | Sprint 2 | Not Started | 0.25 | README P3: sign out
DEV-1 | Device Selection | 1 | University User (Student/Staff/Professor) | view available devices for my department | I can pick equipment that is not already assigned or unavailable | Table lists asset ID, type, manufacturer, model, building, room and status for devices that are unassigned, Active and in my department; assigned/Broken/Repairable devices are not selectable. | Build device_selection.fxml with TableView; query repository by department and availability. | 5 | Sprint 1 | Not Started | 1 | README P1: view available devices
DEV-2 | Device Selection | 1 | University User (Student/Staff/Professor) | see only devices my role (student, staff or professor) is permitted to use | I do not select equipment I am not authorized to check out | Device list is filtered by the device's allowed-roles list set by the admin; a user whose role is not allowed cannot see or assign the device. | Add RoleEligibility check to repository query; add test cases per role. | 3 | Sprint 2 | Not Started | 0.5 | New (admin-granted permissions)
DEV-3 | Device Selection | 2 | University User (Student/Staff/Professor) | filter the list by device type | I can find the kind of equipment I need quickly | Type filter (All, Laptop, Desktop, Smart Board, Laptop Cart, Printer, Router, Network Switch, Other) updates the table instantly. | Add ComboBox filter; use FilteredList on table data. | 2 | Sprint 2 | Not Started | 0.5 | README P2: filter devices
DEV-4 | Device Selection | 1 | University User (Student/Staff/Professor) | assign an available device to myself | I can check out equipment for college work | Selecting a device and clicking Assign sets assigned user, checkout date (today), due date (default loan length, see Reference Data) and marks it unavailable; table refreshes. | Add Assign button; implement AssignmentService.assign(); refresh table. | 5 | Sprint 2 | Not Started | 1 | README P1: assign device
DEV-5 | Device Selection | 1 | University User (Student/Staff/Professor) | be blocked from assigning a device if I have an overdue one, with a clear message | equipment is returned before I receive another device | If any of my devices has a due date before today, Assign is rejected with a message naming the overdue device and due date; no data is changed. | Add hasOverdueAssignment() to EligibilityService; show Alert/inline message. | 3 | Sprint 2 | Not Started | 0.5 | README P1: overdue block + message
DEV-6 | Device Selection | 1 | University User (Student/Staff/Professor) | view the device currently assigned to me | I know what equipment is under my responsibility | A "My Device" panel shows asset ID, model, building/room, checkout date, due date and status; shows "No device assigned" when empty; overdue date highlighted. | Add My Device panel bound to Session user. | 2 | Sprint 2 | Not Started | 0.5 | README P1: view my device
DEV-7 | Device Selection | 1 | University User (Student/Staff/Professor) | update the status of my assigned device to Active, Repairable or Broken | the IT department knows the condition of the equipment | Status dropdown limited to the three allowed values; saving updates the record; a device set to Repairable or Broken becomes unavailable to others. | Add status ComboBox and Save button; call DeviceService.updateStatus(). | 3 | Sprint 2 | Not Started | 0.5 | README P1: update status
DEV-8 | Device Selection | 2 | University User (Student/Staff/Professor) | return my device | it becomes available to another eligible user | Return clears assigned user, checkout and due dates; device is available again if status is Active; my overdue block is lifted. | Add Return button; implement AssignmentService.returnDevice(). | 2 | Sprint 2 | Not Started | 0.5 | README P2: return device
DEV-9 | Device Selection | 4 | University User (Student/Staff/Professor) | receive a confirmation after assigning or returning a device | I know the transaction was completed | Confirmation message shows device asset ID and due date on assign and a return confirmation on return. | Add confirmation Alert/status label. | 1 | Sprint 2 | Not Started | 0.25 | README P4: confirmation
ADM-1 | Admin Dashboard | 1 | Inventory Administrator | view all devices across every department in one table | I can monitor the equipment owned by the college | Table shows asset ID, serial number, type, manufacturer, model, department, building, room, status, assigned user, checkout date and due date; admin-only access. | Build admin_dashboard.fxml with TableView; load all devices from repository. | 5 | Sprint 1 | Not Started | 1 | README P1: view device records
ADM-2 | Admin Dashboard | 2 | Inventory Administrator | filter and search devices by type, department, building, status or serial number | I can find relevant equipment quickly | Filters combine (e.g. Laptops + Nursing + Broken); search box matches serial number or asset ID; Clear Filters resets view. | Add filter controls and search field; use FilteredList with combined predicate. | 3 | Sprint 2 | Not Started | 0.5 | README P2: filter devices
ADM-3 | Admin Dashboard | 1 | Inventory Administrator | create a new device record | new equipment is added to the campus inventory | Form requires asset ID, serial number, type, manufacturer, model, department, building, room and status; duplicate asset ID or serial number is rejected; new row appears in table. | Build create-device form/dialog; add DeviceService.create() with validation. | 5 | Sprint 1 | Not Started | 1 | README P1: create device
ADM-4 | Admin Dashboard | 2 | Inventory Administrator | record each device's building and room on campus | I can tell where equipment is being used | Building is chosen from a set list (see Reference Data); room is free text; both are shown in the table and editable. | Add building ComboBox and room TextField to form and table. | 2 | Sprint 2 | Not Started | 0.5 | README P2: record location
ADM-5 | Admin Dashboard | 1 | Inventory Administrator | choose which user types (Student, Staff, Professor) may use each device | only authorized kinds of users can check out the device | Create/Edit form has Student, Staff and Professor checkboxes; at least one must be selected; saved roles drive what users see on Device Selection (DEV-2). | Add role checkboxes; store allowedRoles on Device; show roles column in table. | 3 | Sprint 2 | Not Started | 0.5 | New (admin-granted permissions)
ADM-6 | Admin Dashboard | 1 | Inventory Administrator | edit an existing device record | inventory information stays accurate when equipment changes | Selecting a row and clicking Edit loads the form; saving updates the record and table; same validation as create. | Reuse create form in edit mode; implement DeviceService.update(). | 3 | Sprint 2 | Not Started | 0.5 | README P1: update device
ADM-7 | Admin Dashboard | 1 | Inventory Administrator | delete a device record after confirming | retired or invalid equipment is removed from inventory | Delete asks for confirmation; a device that is currently assigned cannot be deleted and shows an explanatory message. | Add Delete button with confirmation Alert; add assigned check. | 3 | Sprint 2 | Not Started | 0.5 | README P1: delete device
ADM-8 | Admin Dashboard | 2 | Inventory Administrator | see overdue assignments highlighted | I can follow up with users who have not returned equipment | Rows with a due date before today are highlighted; an overdue counter is shown above the table. | Add row factory styling; add overdue count label. | 2 | Sprint 2 | Not Started | 0.5 | README P2: view overdue
ADM-9 | Admin Dashboard | 1 | Inventory Administrator | have this screen restricted to administrator accounts | create, edit and delete actions cannot be used by students, staff or professors | Non-admin roles cannot open the dashboard; service-layer create/update/delete also reject non-admin callers with a clear message. | Add role guard in SceneManager and DeviceService. | 2 | Sprint 2 | Not Started | 0.5 | README P3: restrict actions

## Sprint Summary
Screen / Epic | Stories | Story Points | Points Done | % Complete | Est. Hours
Foundation | 5 | 14 | 0 | 0% | 2.5
Login | 6 | 13 | 0 | 0% | 2.75
Device Selection | 9 | 26 | 0 | 0% | 5.25
Admin Dashboard | 9 | 28 | 0 | 0% | 5.5
Total | 29 | 81 | 0 | 0% | 16
Sprint | Stories | Story Points | Capacity (pts) | Points vs Capacity | Est. Hours
Sprint 1 | 12 | 39 | 42 | 3 | 7.5
Sprint 2 | 17 | 42 | 42 | 0 | 8.5
Team capacity per sprint (points) | 42
Assumption: capacity of 42 points per sprint is a placeholder; replace with your team's real velocity. Positive 'vs Capacity' = room left.
Assumption: the 16 estimated hours were split across stories in proportion to story points, in 0.25-hour steps.

## Reference Data
Departments | Buildings | User Types (device permissions) | Device Types | Device Status
Computer Science | Science Building | Student | Laptop | Active
Mathematics | Business Building | Staff | Desktop | Repairable
Biology | Humanities Hall | Professor | Smart Board | Broken
Business Administration | Nursing Building | Inventory Administrator | Laptop Cart
English | Library |  | Printer
Nursing | Student Center |  | Router
Library Services | Technology Center |  | Network Switch
IT Services | IT Annex |  | Other
Default loan length (days) | 14
Notes / assumptions:
1. Department, building and loan-length values are assumptions; the README does not list them.
2. Admins are not tied to a department; they can see all departments.
3. Device permissions are set per device by admins (Student / Staff / Professor). A device needs at least one allowed user type.
4. Serial number is a separate field from asset ID; both must be unique.

## Screen Layouts
Screen | Who sees it | Main controls | Table columns / data shown
1. Login | Everyone (before sign-in) | Email field, Password field, Department dropdown, Sign In button, error message label | n/a
2. Device Selection | Student, Staff, Professor | Type filter, Assign button, Return button, Status dropdown + Save, My Device panel, Sign Out | Asset ID, Type, Manufacturer, Model, Building, Room, Status (only available devices permitted for my role in my department)
3. Admin Dashboard | Inventory Administrator | Filters (type, department, building, status), search box, Add/Edit/Delete buttons, device form with allowed-user-type checkboxes, overdue counter, Sign Out | Asset ID, Serial Number, Type, Manufacturer, Model, Department, Building, Room, Status, Assigned User, Checkout Date, Due Date, Allowed User Types